## Budget
Thursday 7 December
Budget
Venues
Fruit | 800
Hull Minster | 450
Warehouse | 400
Vue |  | in film budget
Content
For Luke
Production
Aidan
Estimate | 10000
Access
BSL | 2000
Marketing
Design flyers for delegates | 500
Capture on the day (Photographer) | 600
Flyer design/print | 350
Intercity advertising (Poster sites) | 1000
EDM (with data from others) | 500
Other | 1500
Catering
Breakfast | 600 | £3 x 200
Lunch | 2000 | £10 x 200
Total | 20700
Total Budget | 35000 | Dependant on what Luke has spent already
Remaining | 14300 | For panels/keynotes/travel/accomm

## Timeline
Timeline
2017-07-24
2017-07-31 | Venues confirmed
2017-08-07 | 1/3 of partners in place/Sessions confirmed.
2017-08-14 | Website complete on Hull2017 site
List of key attendees drawn up
2017-08-21 | Budget complete
2017-08-28
2017-08-30 | Hull 2017 Programme Announcement
At least half of the sessions announced and partners in place
Invites land to key attendees
Tickets on sale
2017-09-04
2017-09-11
2017-09-18
2017-09-25
2017-10-02 | Guardian panel annonced, Boiler Room, Vice announce
2017-10-09
2017-10-16
2017-10-23
2017-10-30 | Full programme for Substance announced. Including weekend.
2017-11-06
2017-11-13
2017-11-20
2017-11-27
2017-12-04
2017-12-11
2017-12-18

## Partners
Organisation/Person | Contacting | Notes
The Guardian | Luke B | Helen Pidd, John Harris
Luke working to get them committed by 25 August.
Vice/Noisey | Luke B | The Northern underground or its Grime up North, the new Grime from the North like Bugzy Malone.
Awaiting update
Boiler Room | Luke B | Panel with the new electronic underground - Rival Consoles etc
Will talk to them about Future Forum after securing Warp.
BBC3 (Jeremy Evans) | Martin A first contact
Luke waiting for further email from Jeremy. Sam to follow up to Radio 3 head honcho.
The Creative Society (Martin Bright) | Luke B
Awaiting Update
C4DI hosted panel - | Martin/Luke | Will five bars of internet make
Martin followed up. Steering groups commenced - working on a question.
The Arts Council – Rebecca Horn. Sir Nicolas Serota will be there on the Tuesday night. | Martin A first contact
Luke in conversation with currently.
Designers Republic | Luke B | something hosted on the image of the North?
Update required
The Northern Fiction Alliance | Luke B | already confirmed
Salon North | Luke B | Notions of identity
Wellcome Trust | Martin/Luke | Arts role in public health. Someone from Hull Uni to research? | https://www.theguardian.com/culture/2017/jul/19/arts-can-help-recovery-from-illness-and-keep-people-well-report-says?CMP=share_btn_tw
The Road To Wigan Pier - Daily Mirror campaign
Frank Cottrell Boyce keynote speech | Luke B | keynote speech on Northern culture, post-Brexit
Paul Morley? keynote speech | Luke B
Andy Burnham? keynote speech | Prescott office to approach
Hull2017 - John Pywell / Martin Green | Martin Atkinson
George Osborne | Martin Green
Confirm other panels and find reason to include.
Wilberforce Society
Larkin?

## Schedules
Thursday 7 December
Main Space Panels/Provocations/Keynotes
Time | Venue | Title of Panel | Speaker | Chair | Panelist 1 | Panelist 2 | Panelist 3 | Panelist 4 | Panelist 5
9:00 | Butler Whites/Church | Welcome
10:00 | Hull Minster | Keynote 1
11:00 | The Warehouse | Session 1
12:00 | Fruit | Session 2
13:00 | Lunch
14:00 |  | Session 4
15:00 |  | Session 5
16:00 |  | Session 6
17:00 | Break
18:00 | Summing Up | Hull Minster/Fruit
18:30 | Sessions end
20:00 | Fruit | Performance
Smaller Break Out Discussions
Time | Venue | Title of Session | Speaker
10:30
11:30
12:30
13:30
14:30
15:30
16:30
17:30