## Budget (hidden)
Thursday 7 December
Budget
Venues
Fruit | 800
Hull Minster | 450
Warehouse | 400
Vue |  | in film budget
Content
For Luke
Production
Aidan
Estimate | 10000
Access
BSL | 2000
Marketing
Design flyers for delegates | 500
Capture on the day (Photographer) | 600
Flyer design/print | 350
Intercity advertising (Poster sites) | 1000
EDM (with data from others) | 500
Other | 1500
Catering
Breakfast | 600 | £3 x 200
Lunch | 2000 | £10 x 200
Total | 20700
Total Budget | 35000 | Dependant on what Luke has spent already
Remaining | 14300 | For panels/keynotes/travel/accomm

## Timeline
Timeline
2017-07-24
2017-07-31 | Venues confirmed
2017-08-07 | 1/3 of partners in place/Sessions confirmed.
2017-08-14 | Website complete on Hull2017 site
List of key attendees drawn up
2017-08-21 | Budget complete
2017-08-28
2017-08-30 | Hull 2017 Programme Announcement
At least half of the sessions announced and partners in place
Invites land to key attendees
Tickets on sale
2017-09-04
2017-09-11
2017-09-18
2017-09-25
2017-10-02 | Guardian panel annonced, Boiler Room, Vice announce
2017-10-09
2017-10-16
2017-10-23
2017-10-30 | Full programme for Substance announced. Including weekend.
2017-11-06
2017-11-13
2017-11-20
2017-11-27
2017-12-04
2017-12-11
2017-12-18

## Partners
Organisation/Person | Contacting | Notes | Session Lead
The Guardian | Luke B | Helen Pidd, John Harris
Luke suggesting Anna nmeeting Sam/Martin over Freedom Festival |  | The AND and AND argument
Vice | Luke B | The Northern underground or its Grime up North, the new Grime from the North like Bugzy Malone.
Awaiting update
Noisey | Luke B
Being chased
Huffington Post | Luke B
Being chased
LADbible | Sam
Contacted/getting back to us
Boiler Room | Martin A | Panel with the new electronic underground - Rival Consoles etc
Will talk to them about Future Forum after securing Warp.
BBC3 (Jeremy Evans) | Martin A followed up | Is this the right partner?
Luke waiting for further email from Jeremy. Sam to follow up to Radio 3 head honcho.
The Creative Society (Martin Bright) | Luke B
Awaiting Update
C4DI hosted panel - | Martin/Luke | Will five bars of internet make people less lonely. What is a creative industry?
Martin followed up. Steering groups commenced - working on a question.
The Arts Council – Rebecca Horn. Sir Nicolas Serota will be there on the Tuesday night. | Martin A first contact
Luke in conversation with currently. | Sam in contact with Jessica Farmer/Luke in contact with Rebecca Horn
Designers Republic | Luke B | How do we sell the north?
Update required
The Northern Fiction Alliance / Wrecking Ball Press | Luke B | NFA Luke confirmed and going to speak to Shane
Martin Bedford (Leeds), Sean O'Brien (set in Newcastle and Hull) |  | The role of a northern voice / future northern novellists / how can joined up publishing
Salon North | Luke B | Notions of identity
Wellcome Trust | Martin/Luke | Arts role in public health. Someone from Hull Uni to research? |  | https://www.theguardian.com/culture/2017/jul/19/arts-can-help-recovery-from-illness-and-keep-people-well-report-says?CMP=share_btn_tw
| Not contacted yet | CCG
The Space |  | How does a city or town's cultural product hit a global audience?
CANVAS | Sam H
With Boiler Room / The Space
Frank Cottrell Boyce keynote speech | Luke B | keynote speech on Northern culture, post-Brexit
Why?
Paul Morley: host/chair | Luke B
Confirmed
Humber LEP | Martin A | Ensure that the Humber capitalises on the economic opportunities offered by Hull: UK City of Culture 2017.
Tim Rix |  | Be on a panel addressing this specific issue and how that is happening.
sIEMENS, gREEN pORT |  | Work with Hull: UK City of Culture 2017 to ensure that the ‘place’ context is wider than Hull and encompasses and capitalises on the Humber opportunities. The Investment and Delivery Plan requests LGF funding to support Quality of Place Investment and a Gallery, Conference and Exhibition Centre in Hull. LGF support is also requested in the Investment and Delivery Plan to significantly enhance the economic and social benefits of the Humber Bridge visitor offer.
Miranda Sawyer | Luke B
Almost confirmed
Culture Liverpool / Cities of the North | Martin A | Chris working from Cities of the North has confirmed. ShOuld choose who to get from Culture Liverpool and add to what makes a City of Culture a success?
Council of the North |  | Will the Council of the north succeed where previous inititatives haven't and why?
What we want to build is a representative a body of council leaders, businesses and MPs – alongside trade unions and the community and voluntary sector.
Andy B
University of Hull |  | Logistics?
Hack and Host |  | ‘artists as political activists’ in coversation with Jeremy Deller
Policy North |  | Contact by MA
Andy Burnham? keynote speech | Prescott office to approach
Hull2017 - John Pywell / Martin Green | Martin Atkinson | The next 25 years of Culture in Hull
George Osborne | Martin Green
Confirm other panels and find reason to include.
Wilberforce Society
Blast Theory
Luke
Hold off
Martin/Sam

## Schedules
Thursday 7 December
Main Space Panels/Provocations/Keynotes
Time | Venue | EM | Schedule | Hosted By | Question | Producer | Session Lead | Chair | Panelist 1 | Panelist 2 | Panelist 3 | Panelist 4 | Panelist 5
9:30 | Humber Street |  | Welcome | Martin Green & younger voice
10:00-10:20 | Humber Street Gallery |  | Keynote 1 and move on to next venue. Explanation on how the day works | Hull 2017/Substance: Welcome |  | Martin A |  | Niki Bedi
10:30-11:15 | 1@ the dock |  |  | CCG/Hull 2017 | How arts can save the NHS An all-party enquiry this summer showed how a thriving arts and culture scene has a huge impact on the health and well being of any town or city, leading to a fall in hospital admissions. Can arts relieve the pressure on the NHS? | Martin A | Hull 2017 | Niki Bedi | Nicky Taylor: Theatre and Dementia Research Associate at West Yorkshire Playhouse who has pioneered the way for dementia friendly performances. | Upswing: Victoria Amedume to talk about the work in Hull | Alex Mitchell: Silent Uproar | Dr Dan Roper: CCG : Dan Roper was born in Hull. After graduating at Edinburgh University he completed his GP training in Hull. He was a local GP for 30 years and was GP Principal at Springhead Medical Centre. Dan cares deeply about improving the city’s health and has a long history of working with local organisations to promote health issues and equality of opportunity. Dan has been involved in GP education for the last 25 years.
10:45-11:30 | Fruit |  | CHECK TIME IS OK WITH PANELLISTS | The Space/Susannah Simons | Tell The World How digital integration can build new and global audiences. Opera North, The Hepworth in Wakefield, Daniel Elms (New Sound Collective), Katherine Jewkes (MIF/Space) discuss how embracing digital technologies can bring new and global audiences to artists and work. | Martin A |  | Susannah Simons | Daniel Elms (New Sound Collective and Hull born artist) | Katherine Jewkes (MIF and The Space) | Nina Rogers (Yorkshire Sculpture Park) | Dominic Gray (Opera North)
11:00-11:45 | C4DI Theatre |  |  | Hack and Host: Jeremy Deller | Art can change the world How the arts are driving political, social and economic change. The Turner Prize has always been an event that has always been at the centre of controversy and previous Turner Prize nominees have pushed boundaries which have led to social and political change. Hull based artist collective Hack and Host explore how the creative sector is a vehicle for political, social and economic change using their campaign shop that will be open from 5 – 8 December. Northern culture has always challenged the establishment; how do we continue to do this as we face Brexit and an increasingly divided world? | Martin A | Kate West | Hack & Host | Bill Drummond
11:30 - 12:15 | 1@ the dock |  |  | Hull Univeristy | How to avoid an identity crisis Hullness revisited. Hullness was referred to by the UK City of Culture selection panel and the spirit of local identity has underpinned much of the 2017 cultural programme. At the end of a phenomenal year, the way that Hull is perceived by external observers has undoubtedly changed. But what does this mean to those who live here? In this discussion, we revisit Hullness to ask if a year in the spotlight has changed what people think about what their city is, and what it could be in the future? And we explore how an international city can retain its identity and sense of pride on a local scale. | Martin A |  | Niki Bedi | Dr Jo Byrne – Research Manager, Culture, Place and Policy Institute (CPPI), University of Hull | Professor David Atkinson – Professor of Cultural and Historical Geography, University of Hull | Visit Britian Rep | Rough Gudies
12:30 - 13:30 | Hull Minster |  | Lunch
13:30 - 14:20 | Hull Minster |  | Keynote |  | Guardian Live in Conversation |  |  | John Harris
14:45 - 15:30 | C4DI Theatre |  |  | Hull 2017 | Show me the money! Culture and business: the benefits of investment in culture. Hull 2017 raised more corporate money for its year as city of culture than the London Olympics did for the Cultural Olympiad. The benefits of working with a range of businesses and organisations whose investment in City of Culture go far beyond the obvious. The discussion focuses on the crucial nature of this investment and highlights the benefits to place, people and the local economy when business and culture find the correct synergy. | Martin A | Sussanah Simons | Sussanah Simons | Dominic Gibbons (Wykeland) | Francesca Heygi (Hull 2017) | Pat Connor: Head of BBC Development & Events, UK & Director, BBC South West | KCOM: Cathy Phillips: Director of Marketing cathy.phillips@kcom.com | Kevin Moore Humber Bridge | https://www.hudgellsolicitors.co.uk/the-hudgell-solicitors-trust/ Jo Hudgell jo@hudgell.karoo.co.uk
15:00 - 15:45 | Fruit |  |  | BBC Academy | From stage to screen BBC Arts and Channel 4’s Random Acts discuss routes into being commissioned for broadcast. BBC Arts, and a panel comprised of the UK’s leading arts broadcasters share their insights into connecting with arts organisations and how digital changes are impacting their decisions. | Martin A |  | Niki Bedi | Sky Arts Producer: Rocio Cano | Jeremy Routledge: Calling the Shots: Channel 4 Random Acts | BBC Arts: Lamia Dabboussy is the Editor for BBC Arts | Peter Groom: Commissioned Random Acts Artist
15:15 - 16:00 | 1@ the dock |  |  | C4DI | HullOS v2042gm – your City evolved. Connected, Accelerated and Accepted How technology transformed the city you knew. The future (like the past) is defined by technology – and we own it. Members of the Hull C4DI (Centre for Digital Innovation) have combined their knowledge, expertise and imagination to define a future narrative for a city. Using Hull as a case study their approach has been based around 4 views: Hull's current resources and unique selling points. Hull's current challenges. Project Hull's resources in 20 years. Apply the future resources to address many of Hull's current challenges. As part of the session we will also address how technology is not only changing a city's operations, but also how technology is being applied to arts and culture. | Martin A | C4DI | David Keel / Sarah Louise | Blast Theory | C4DI | C4DI | C4DI
15:30 - 16:15 | Fruit |  |  | British Council/Warren | It’s a little bit leave it How the next generation of artists are responding to Brexit and see their future. When the decision wasn’t yours, but the impact will be life-long... we discuss the concerns of younger people across the north. This group will address the findings of the Next Generation UK commissioned by The British Council and carried out by Demos which surveyed young people across the country on their views about their future in the world and that of the UK’s following the EU referendum, addressing the findings and recommendations through interviews, spoken word and discussions. Hosted by spoken word artist Joe Hakim and young people from The Warren Project Hull. | Martin A | Joe Hakim | The Warren | The Warren | The Warren | The Warren | British Council Rep/Demos | Emma Hardy MP
15:45 - 16:30 | C4DI Theatre |  |  | The Quietus | What is the role of a capital city? London calling? Not anymore. Why musicians are better off away from the capital. The Quietus lead a discussion about whether London is really the best place for musicians and artists. | Sam Hunt / Luke B | The Quietus | Anna Wood
16:00 - 16:45 | 1@ the dock |  |  | British Council / Cities of Culture / Martin Green | You’re only here for the Culture What’s the point of a city of Culture? What are the measures of success for a city of culture? How does this manifest and what is the promise in relation to the reality? Are they brilliant examples of culture as a change agent or an apology in disproportionate levels of arts funding? The panel will be comprised of representatives from previous cities of culture. | Sam Hunt |  | Pete Massey | Martin Green | Bob Palmer | Shona McArthy | Chris Baldwin - Creative Director Galway 2020 European Capital of Culture
17:00 - 17:45 | Fruit |  |  | Northern Fiction Alliance | Northern Souls Northern Fiction Alliance lead a discussion on how independent publishers and new voices are flourishing in the North, and how there has never been a better time to get your voice heard in the North. | Sam Hunt / Luke B | Northern Fiction Alliance | NFA | Nichola or Stefan - And Other Stories (Sheffield) | Jacob Ross - Peepal Tree (Leeds) | Shane Rhodes - Wrecking Ball Press (Hull) | Valley Press (Sunderland)
17:15 - 18:00 | C4DI Theatre |  |  | Blast Theory | We Made Ourselves Over For the last 18 months pioneering artists Blast Theory have been working with experts and residents in Hull and Aarhus to imagine a future city in 80 years time. Their project 2097: We Made Ourselves Over culminated in October and November with free public screenings of their short sci-fi films and immersive experiences imploring people to think about what they want for the future. Hear what Blast Theory have discovered on their journey and how we can work to achieve these future cities, as Blast Theory are joined by some of the experts they've worked with throughout the process. | Hannah W/Sam Hunt | Blast Theory
18:15 - 18:45 |  |  |  | Final Session/Drinks
19:00 | Sessions end |  | Fruit | DRINKS: MULLED WINE
20:00 | Fruit |  | Performance
Sessions to find homes for
Katy Fuller | Site Specific works
15 minutes Provocations with 15 mins Q&A (smaller capacities)
Time | Venue |  | Title of Session | Speaker | Chair
11:30 | C4DI Theatre
12:30 | C4DI Theatre
13:30 | C4DI Theatre
14:30 | C4DI Theatre
15:30 | C4DI Theatre
16:30 | C4DI Theatre
17:30 | C4DI Theatre
11:00-12:00 | The Warehouse
A session around the impact of site specific or large scale outdoor work and the benefit they bring to place.

## Panellists Contacts
Thursday 7 December
Main Space Panels/Provocations/Keynotes
Time | Venue | Schedule | Hosted By | Question | Producer | Session Lead | Chair | Panelist 1 | Panelist 2 | Panelist 3 | Panelist 4 | Panelist 5
9:30 | Humber Street | Welcome | Martin Green & younger voice
10:00-10:20 | Humber Street Gallery | Keynote 1 and move on to next venue. Explanation on how the day works | Culture, creativity and future of the north from young strong northern artist - Lauren Laverne, Kate Tempest, Maxine Peake - similar) |  | Martin A |  | Amy Garcia/Nikki Bedi
Email | [6 empty] | amy.garcia@bbc.co.uk
Phone | [6 empty] | 7740739839
10:30-11:15 | 1@ the dock |  | CCG/Hull 2017 | How arts can save the NHS An all-party enquiry this summer showed how a thriving arts and culture scene has a huge impact on the health and well being of any town or city, leading to a fall in hospital admissions. Can arts relieve the pressure on the NHS? | Martin A | Hull 2017 | Amy Garcia/Nikki Bedi | Nicky Taylor: Theatre and Dementia Research Associate at West Yorkshire Playhouse who has pioneered the way for dementia friendly performances. | Upswing: Victoria Amedume to talk about the work in Hull | Alex Mitchell: Silent Uproar | Dr Dan Roper: CCG : Dan Roper was born in Hull. After graduating at Edinburgh University he completed his GP training in Hull. He was a local GP for 30 years and was GP Principal at Springhead Medical Centre. Dan cares deeply about improving the city’s health and has a long history of working with local organisations to promote health issues and equality of opportunity. Dan has been involved in GP education for the last 25 years.
Email | [6 empty] | amy.garcia@bbc.co.uk | nicky.taylor@wyp.org.uk | vicki@upswing.org.uk | alex.mitchell@silentuproarproductions.co.uk | daniel.roperccg@nhs.net
Phone | [6 empty] | 7740739839 | 7888723429 | 7939027444 | 7855801234 | 7760270467
10:45-11:30 | Fruit | CHECK TIME IS OK WITH PANELLISTS | The Space/Susannah Simons | Tell The World How digital integration can build new and global audiences. Opera North, The Hepworth in Wakefield, Daniel Elms (New Sound Collective), Katherine Jewkes (MIF/Space) discuss how embracing digital technologies can bring new and global audiences to artists and work. | Martin A |  | Susannah Simons | Daniel Elms (New Sound Collective and Hull born artist) | Katherine Jewkes (MIF and The Space) | Nina Rogers (Yorkshire Sculpture Park) | Dominic Gray (Opera North)
Email | [6 empty] | susannah.simons@bravebison.io | info@danielelms.co.uk | katherine.jewkes@mif.co.uk | nina.rogers@ysp.org.uk | dominic.gray@operanorth.co.uk
Phone | [6 empty] | 44 773 648 1163 | 07731 587989 |  |  | 07970 463175
11:00-11:45 | Pier Street |  | Hack and Host: Jeremy Deller | Art can change the world How the arts are driving political, social and economic change. The Turner Prize has always been an event that has always been at the centre of controversy and previous Turner Prize nominees have pushed boundaries which have led to social and political change. Hull based artist collective Hack and Host explore how the creative sector is a vehicle for political, social and economic change using their campaign shop that will be open from 5 – 8 December. Northern culture has always challenged the establishment; how do we continue to do this as we face Brexit and an increasingly divided world? | Martin A | Kate West | Kate West: Hack & Host | Bill Drummond
Email | [6 empty] | kate.west@hull2017.co.uk
Phone | [6 empty] | 7708510727
11:30 - 12:15 | 1@ the dock |  | Hull Univeristy | How to avoid an identity crisis Hullness revisited. Hullness was referred to by the UK City of Culture selection panel and the spirit of local identity has underpinned much of the 2017 cultural programme. At the end of a phenomenal year, the way that Hull is perceived by external observers has undoubtedly changed. But what does this mean to those who live here? In this discussion, we revisit Hullness to ask if a year in the spotlight has changed what people think about what their city is, and what it could be in the future? And we explore how an international city can retain its identity and sense of pride on a local scale. | Martin A |  | Amy Garcia | Dr Jo Byrne – Research Manager, Culture, Place and Policy Institute (CPPI), University of Hull | Professor David Atkinson – Professor of Cultural and Historical Geography, University of Hull | Visit Britian Rep | Rough Gudies
Email | [7 empty] | j.byrne@hull.ac.uk | david.atkinson@hull.ac.uk
Phone
12:30 - 13:30 | Hull Minster | Lunch
13:30 - 14:20 | Hull Minster | Keynote |  | Guardian Live in Conversation |  |  | John Harris
14:45 - 15:30 | C4DI Theatre |  | Hull 2017 | Show me the money! Culture and business: the benefits of investment in culture. Hull 2017 raised more corporate money for its year as city of culture than the London Olympics did for the Cultural Olympiad. The benefits of working with a range of businesses and organisations whose investment in City of Culture go far beyond the obvious. The discussion focuses on the crucial nature of this investment and highlights the benefits to place, people and the local economy when business and culture find the correct synergy. | Martin A | Sussanah Simons | Sussanah Simons | Dominic Gibbons (Wykeland) | Francesca Heygi (Hull 2017) | Pat Connor: Head of BBC Development & Events, UK & Director, BBC South West | KCOM: Kathy Phillips: Director of Marketing cathy.phillips@kcom.com | Kevin Moore Humber Bridge | https://www.hudgellsolicitors.co.uk/the-hudgell-solicitors-trust/ Jo Hudgell jo@hudgell.karoo.co.uk
Email | [6 empty] | susannah.simons@bravebison.io |  | fran.hegyi@hull2017.co.uk | pat.connor@bbc.co.uk |  | kevin.moore@humberbridge.co.uk
Phone | [6 empty] | 44 773 648 1163
15:00 - 15:45 | Fruit |  | BBC Academy | From stage to screen BBC Arts and Channel 4’s Random Acts discuss routes into being commissioned for broadcast. BBC Arts, and a panel comprised of the UK’s leading arts broadcasters share their insights into connecting with arts organisations and how digital changes are impacting their decisions. | Martin A | Amy Garcia | Nikki Bedi | Sky Arts Producer: Rocio Cano | Jeremy Routledge: Calling the Shots: Channel 4 Random Acts | BBC Arts: Lamia Dabboussy is the Editor for BBC Arts | Peter Groom: Commissioned Random Acts Artist
Email | [7 empty] | rocio.cano@storyvault.tv | jeremy@callingtheshots.co.uk |  | petergroom01@gmail.com
Phone
15:15 - 16:00 | 1@ the dock |  | C4DI | HullOS v2042gm – your City evolved. Connected, Accelerated and Accepted How technology transformed the city you knew. The future (like the past) is defined by technology – and we own it. Members of the Hull C4DI (Centre for Digital Innovation) have combined their knowledge, expertise and imagination to define a future narrative for a city. Using Hull as a case study their approach has been based around 4 views: Hull's current resources and unique selling points. Hull's current challenges. Project Hull's resources in 20 years. Apply the future resources to address many of Hull's current challenges. As part of the session we will also address how technology is not only changing a city's operations, but also how technology is being applied to arts and culture. | Martin A | C4DI | David Keel / Sarah Louise | Blast Theory | C4DI | C4DI | C4DI
Email
Phone
15:30 - 16:15 | Fruit |  | British Council/Warren | It’s a little bit leave it How the next generation of artists are responding to Brexit and see their future. When the decision wasn’t yours, but the impact will be life-long... we discuss the concerns of younger people across the north. This group will address the findings of the Next Generation UK commissioned by The British Council and carried out by Demos which surveyed young people across the country on their views about their future in the world and that of the UK’s following the EU referendum, addressing the findings and recommendations through interviews, spoken word and discussions. Hosted by spoken word artist Joe Hakim and young people from The Warren Project Hull. | Martin A | Joe Hakim | The Warren | The Warren | The Warren | The Warren | British Council Rep/Demos | Emma Hardy MP
Email
Phone
15:45 - 16:30 | C4DI Theatre |  | The Quietus | What is the role of a capital city? London calling? Not anymore. Why musicians are better off away from the capital. The Quietus lead a discussion about whether London is really the best place for musicians and artists. | Sam Hunt / Luke B | The Quietus | Anna Wood
Email
Phone
16:00 - 16:45 | 1@ the dock |  | British Council / Cities of Culture / Martin Green | You’re only here for the Culture What’s the point of a city of Culture? What are the measures of success for a city of culture? How does this manifest and what is the promise in relation to the reality? Are they brilliant examples of culture as a change agent or an apology in disproportionate levels of arts funding? The panel will be comprised of representatives from previous cities of culture. | Sam Hunt |  | Pete Massey | Martin Green | Bob Palmer | Claire Mccolgan | Chris Baldwin - Creative Director Galway 2020 European Capital of Culture | Shona McArthy
Email | [7 empty] | martin.green@hull2017.co.uk |  |  | chris@Galway2020.ie
Phone
17:00 - 17:45 | Fruit |  | Northern Fiction Alliance | Northern Souls Northern Fiction Alliance lead a discussion on how independent publishers and new voices are flourishing in the North, and how there has never been a better time to get your voice heard in the North. | Sam Hunt / Luke B | Northern Fiction Alliance | NFA | Nichola or Stefan - And Other Stories (Sheffield) | Jacob Ross - Peepal Tree (Leeds) | Shane Rhodes - Wrecking Ball Press (Hull) | Valley Press (Sunderland)
Email
Phone
17:15 - 18:00 | C4DI Theatre |  | Blast Theory | We Made Ourselves Over For the last 18 months pioneering artists Blast Theory have been working with experts and residents in Hull and Aarhus to imagine a future city in 80 years time. Their project 2097: We Made Ourselves Over culminated in October and November with free public screenings of their short sci-fi films and immersive experiences imploring people to think about what they want for the future. Hear what Blast Theory have discovered on their journey and how we can work to achieve these future cities, as Blast Theory are joined by some of the experts they've worked with throughout the process. | Hannah W/Sam Hunt | Blast Theory
18:15 - 18:45 |  |  | Final Session/Drinks
19:00 | Sessions end | Fruit | DRINKS: MULLED WINE
20:00 | Fruit | Performance
Sessions to find homes for
15 minutes Provocations with 15 mins Q&A (smaller capacities)
Time | Venue | Title of Session | Speaker | Chair
11:30 | C4DI Theatre
12:30 | C4DI Theatre
13:30 | C4DI Theatre
14:30 | C4DI Theatre
15:30 | C4DI Theatre
16:30 | C4DI Theatre
17:30 | C4DI Theatre
11:00-12:00 | The Warehouse
A session around the impact of site specific or large scale outdoor work and the benefit they bring to place.

## Schedules (2)
| Travel | Accommodation | Travel Arrangements | Hotel Arrangements
Question
Northern Souls Northern Fiction Alliance lead a discussion on how independent publishers and new voices are flourishing in the North, and how there has never been a better time to get your voice heard in the North.
Art can change the world How the arts are driving political, social and economic change The Turner Prize has always been an event that has always been at the centre of controversy and previous Turner Prize nominees have pushed boundaries which have led to social and political change. Hack and Host explore how the creative sector is a vehicle for political, social and economic change
HullOS v2042gm – your City evolved. Connected, Accelerated and Accepted How technology transformed the city you knew. The future (like the past) is defined by technology – and we own it. We have imagined that around the year 2042, a resident of Hull buried a time-capsule containing future artefacts from their surroundings. In the year 2017 we dug it up early and opened the box. Members of the Hull C4DI (Centre for Digital Innovation) have combined their knowledge, expertise and imagination to define a future narrative for Hull. Their approach has been based around 4 views: a) Hull’s current resources and unique selling points. b) Hull’s current challenges c) Project Hull’s resources into a 20+ year future d) Apply the leveraged future resources to address many of Hull’s current challenges.
How to make a successful city of culture?
How arts can save the NHS An all-party enquiry this summer showed how a thriving arts and culture scene has a huge impact on the health and well being of any town or city, leading to a fall in hospital admissions. Can arts relieve the pressure on the NHS?
It’s a little bit leave it How the next generation of artists are responding to Brexit When the decision wasn’t yours, but the impact will be lifelong, we discuss the concerns of Brexit with younger people across the north. This group will address the findings of the Next Generation UK research commissioned by The British Council and carried out by Demos, which surveyed young people across the country on their views of the UK, addressing the findings and recommendations through interviews, spoken word and discussions.
How arts and business can find a working relationship with benefits beyond the obvious
London calling? Not anymore. Why musicians are better off away from the capital. The Quietus lead a discussion about whether London is really the best place for musicians and artists.
How do artists reach a global audience, and how does that benefit their hometown?
Panel of individuals gathered together by the Guardian to sum up and publish an article of the summing up
Chair

## Schedule by Venue
Venue | Question | Capacity | EM | HPSS | Production | All Occasions
Humber Street Gallery
09:30 - 10:20 | Welcome and Briefing |  | Joanna M | 0 | Vocal PA and mic
1 @ The Dock |  | Max. 170 | Danni H |  | Full PA, 6way wireless mics, HPSS LX, plus 20m of Pipe and Drape. Projector and screen, laptop for powerpoint | 130 - 170 Chairs
10:30 - 11:15 | How Arts Can Save the NHS |  | Danni H | 1
11:30 - 12:15 | How To Avoid An Identity Crisis |  | Danni H | 1
15:15 -16:00 | HullOS v2042gm – your City evolved. Connected, Accelerated and Accepted |  | Danni H | 1
16:00 - 16:45 | You're Only Here For The Culture |  | Danni H | 1
Fruit |  | 150 |  |  | In house PA + HPSS desk, 6way wireless mics, in house LX, 2x 55inch LCD on stands, laptop for powerpoints | /
7:00 | Access
10:45 - 11:30 | Tell The World |  | Liv H ? | 2
15:00 - 15:45 | From Stage To Screen |  | Liv H ? | 2
17:00 - 17:45 | Northern Souls |  | Liv H ? | 2
20:00 | Performance and After-Party
Pier Street |  | 30 |  |  | Full PA, 6way wireless mics, HPSS LX, 2x 55inch LCD on stands, laptop for powerpoints | 30 Chairs
11:00 - 11:45 | How Art Can Change The World |  | Joanna M | 3
Hull Minster
12:30 - 13:30 | Lunch | A Section: 250 | Danni H | 2 | Full PA, 6way wireless mics plus some band/performance equipment, HPSS LX, large screen and projector.
13:30 - 14:30 | Keynote | B section: 100 | Danni H | 1 | Full PA, 6way wireless mics, 1x LCD and powerpoint laptop
17:00 | Out
C4Di Theatre
14:45 - 15:30 | Show Me The Money |  | Joanna M | 3
15:45 - 16:30 | What Is The Role Of A Capital City? |  | Joanna M | 3
17:15 - 18:00 | We Made Ourselves Over |  | Joanna M | 3

## Venue Contacts
Venue | Name | Email | Number | Capacity
Fruit | Joe Hubbard | joe@fruitspace.co.uk | (0)7875971439
Hull Minster | Jane Owen | bryony@bryony.karoo.co.uk
C4DI Theatre | Dileepa Ranawake | dr@c4di.net | (0)7446698735
1@TheDock | Tom Watson | taw@wykeland.co.uk | 01482 320968 |  | We have keys for 1athedock so liaise with Aidan and Rachel B
Pier Street
Humber Street Gallery | Louis | louis.jones@hull2017.co.uk