## Risk Log
Risk Register
Project name: |  | Story Box Circus
Project manager: |  | Matthew Woodford
ID | Date raised | Risk description | Likelihood | Impact | Owner | Mitigating plan | Response and actions
1 | 2017-09-15 | Loss of care home | Medium | High | Matthew Woodford & Cian Smyth | Clear communication lines between care home and Upswing. A contact list of backup care homes is kept who have shown some interest in the project, and could be contacted to back up. | Upswing and Hull UK City of Culture 2017 will use the list of backup care homes to secure a replacement.
2 | 2017-09-15 | Incident with a participant requiring medical assistance | Medium | Low | Production Manager & Matthew Woodford | Artist-educators are experienced in handling difficult situations which occur in a care home.Artist-educators are trained in health and saftey procedures. Risk Assessments will be carried out at each care home, which artist-educators will have before they reach the homes. All artist educators are told to read Risk Assessments beforehand. | The Production Manager will stop the activity and hand over to care home staff to lead the situation. The Production Manager and Matthew Woodford will decide if it is safe to continue with activities in that care home. Show reports are conducted each evening by every Artist-Educator, to log incients and responses. Production Manager and Producer will periodically review show reports to discuss if these responses were adequte, and whether new processes need to be put in place.
3 | 2017-09-15 | A incedent where a participant becomes aggressive or voilent. | Medium | Low | Production Manager & Matthew Woodford | Artist-Educators are experienced in handling difficult situations which occur in care homes. Everybody is trained in health and saftey procedures. Risk Assessments will be carried out at each care home, which artist educators will have before they reach the home. All artist educators are told to read Risk Assessments beforehand. | The Production Manager will stop the performance and hand over to care home staff to lead the situation. The production manager and producer will make a joint decision about whether it is safe to continue with activities in that care home.
4 | 2017-09-15 | An major unforseen cost to the project. | Medium | High | Matthew Woodford | Clear control of outgoings to manage budgets, flexibility and contingency in finance, thorough project and budgetry planning. | Upswing will take the cost out of contingency funds or company reserves.
5 | 2017-09-15 | A care home is an unsafe working environment for the Upswing team | Low | Low | Production Manager & Matthew Woodford | All care homes are checked during site visits to ensure a safe working environment. All care homes are satisfactory rated by the quality care commision. | Production Manager and Producer will make the joint decision about whether it is safe to continue with the activities at the care home. If it is not safe, the activities will stop.
6 | 2017-09-15 | Artist-Educator is unable to deliver activities on a given day due to illness. | Medium | Low | Production Manager + Matthew Woodford | The workshop and performance is flexible, and able to be performed by less members of the creative team. | The activity will go ahead without the sick Artist-Educator.
7 | 2017-09-15 | Artist-Educator is unable to deliver activities on a given day due to injury. | Medium | Low | Production Manager + Matthew Woodford | Artist-Educators are trained and experienced in delivering activities in a way to mimimalise injury to themselves. | Artist-Educator will receive immediate medical attention. An adapted version of the activity will go ahead without the injured party.
8 | 2017-09-15 | An Artist-Educator has to withdraw from the project due to circumstances beyond their control. | Medium | Medium | Matthew Woodford | Upswing regually update their pool of trusted contacts. Time has been worked into the schedule to allow for time to redevelop the project with a member missing. Each artist educator is multi-skilled, and adaptable to a number of different roles within the project. Thorough handover for all key roles. | Upswing will EITHER a)find a replacement based on their pool of experienced Artist-Educators OR b) resculpt the performance and workshop to ensure the project can still be delivered, without impeeding the artsitic credibility and participant outcomes.
9 | 2017-09-15 | A loss of transport on a given day, causing distruption to the schedule. | Medium | Low | Production Manager | Production Manager will ensure the vehical is in good working order before the project begins. Upswing will use a hire company, with an agreement for replacement transportation should a vehicle break down. | Production Manager will organise alternative transportation with the hire company. If there is a delay to leading an activity, the Production Manager will communicate this to the care home. If no alternative transport can be found on that day, Production Manager will rearrange a date where we can deliver the activities in the care home.