|  |  |  |  |
| --- | --- | --- | --- |
|  | **Greatfield 60 Years On – Production Schedule** |  |  |
| **Dates** | **Activity** | **STATUS** | **NOTES** |
|  |  | COMPLETE / ON-TIME / BEHIND |  |
| Aug. – Dec. 2016 | Planning for and delivery of **community TV production course** in partnership with Estuary TV |  | We were unsuccessful with an external application for this aspect of the project. We are currently looking at alternatives. WEA appears to be the best option. Estuary TV have support us with new reporting. |
| January 2017 | Opening of pop-up-gallery. Launch event and promotion of **Greatfield 60 Years On** including introducing plans for a community garden and other environmental works for Greatfield.  First community TV shorts screenings. Start weekly ‘Creativity begins at Home’ workshops  **Teatime Talk 1**  –About Greatfield famous son Mick Ronson |  | Launch event (27th January 2017) Gallery open and good response to the first exhibition. Garden project begin at 2 venues on the estate. ‘Creativity Begins at Home’ (now ‘Crafty Cuppa’), ‘Family Fun’ and ‘Greatfield Quilt’ sessions happening weekly.  ‘Turn and Face the Strange’ Mick Ronson Story-gathering workshop took place on 10th Feb also ‘This is Your Life’ oral history workshop (20th Feb). |
| February 2017 | Begin to build curated collection of Greatfield photographs to be displayed at the pop-up gallery.  Weekly ‘Creativity begins at Home’ workshops  **Teatime Talk 2** |  | ‘Greatfield Wall’ of donated photographs it looking amazing already.  Teatime Talk – ‘Afternoon at the Soaps’ Marvin Close. |
| March 2017 | **Recruitment of volunteers and participants** for ‘Art in a Cart’ workshops.  Workshop planning/materials purchased.  TV shorts screenings. Weekly ‘Creativity begins at Home’ workshops  **Teatime Talk 3** |  | Art in a Cart recruitment and schedule produced. Materials bought and ‘cart’ created.  Weekly sessions continue.  New session ‘Big Local pop-in’ to start 15th March 2017 and take place every Wednesday. |
| April - May 2017 | Delivery of **‘Art in a Cart’ workshops** at sites around Greatfield throughout April and May. Exhibition of ‘Boxes of Beauty and Hope’ at the pop-up gallery. Weekly ‘Creativity begins at Home’ workshops  **Teatime Talk 4-5** |  |  |
| June 2017 | **‘Freedom from Worry’ carnival costume** **workshop**s delivered with local schools and community groups.  TV shorts screenings. Weekly ‘Creativity begins at Home’ workshops  **Teatime Talk 6** |  |  |
| July – September 2017 | **Planning, preparation and promotion** of Street Party event  **Street Party** with screenings, family activities, carnival costume parade and dance performances.  Weekly ‘Creativity begins at Home’ workshops  **Teatime Talk 7-9** |  |  |
| October - December 2017 | **End party will act as official launch** of new community garden/environmental works for Greatfield including new permanent artworks/art trail.  Weekly ‘Creativity begins at Home’ workshops.  **Exhibition of photography** done through the year.  TV shorts screenings  **Teatime Talk 11-12** |  |  |
| January – February 2018 | **Evaluation** of Greatfield 60 Year On including continuation plans. |  |  |