|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Les Motherby |
| **Name of Project** | Tiger Rags - The fabric of Hull City AFC |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
| 01/07/2016 | 31/07/2016 | Planning activity with collectors/HCST | COMPLETE / ON-TIME / BEHIND |  |
| 01/07/2016 | 31/07/2016 | Planning activity with Streetlife |  |  |
| 01/07/2016 | 31/07/2016 | Planning activity with Age UK |  |  |
| 01/08/2016 | 31/08/2016 | Final decision on artifact content |  |  |
| 01/09/2016 | 30/09/2016 | Artwork and text creation for banner |  |  |
| 01/01/2017 | 31/01/2017 | Approach prospective speakers |  |  |
| 01/02/2017 | 14/02/2017 | Purchase of mannequins |  |  |
| 01/03/2017 | 03/03/2017 | Printing of banners and display material |  |  |
| 01/03/2017 | 31/03/2017 | Audio transcription of banners and display material |  |  |
| 01/03/2017 | 31/03/2017 | Approach and brief local media |  |  |
| 01/03/2017 | 31/05/2017 | 1st stage web/social media promotion |  |  |
| 01/06/2017 | 01/10/2017 | Massive all platform promotion of event |  |  |
| 20/06/2017 | 31/06/2017 | Deliver exhibits/material to Streetlife |  |  |
| 01/07/2017 | 30/09/2017 | Streetlife Museum exhibition |  |  |
| 01/10/2017 | 01/10/2017 | Age UK reminiscence event |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances