## 2017
Pezo von Ellrichshausen + Felice Varini 'A Hall for Hull'
MONTH | DAY | DATE | Setworks | Project Team | Felice Varini | Pezo von Ellrichshausen | 128a | Press and events
| Friday | 15 | Dan & others arrive, crane training, Dan to get key for Staples storage for barrier delivery
| Saturday | 16 | Tim arrives, deliveries to Staples | Andrew Knight available if reqd
| Sunday | 17 | Setworks on site, site inspection barriers, laying out, first towers delivery | Andrew Knight on site
| Monday | 18 | Setworks on site, first towers erected. | Hazel Colquhoun, Andrew Knight on site AK available in evening if reqd | Delivery of projector to Hull Minster offices.
| Tuesday | 19 | Setworks on site, second towers delivery 8am | Anna Holsgrove, Sam Wilkinson on site, Hazel Colquhoun on site until 2pm, Andrew Knight after 11am if reqd
| Wednesday | 20 | Setworks on site, third towers delivered 8am, second towers erected by end of day FULL TEAM SITE MEETING 4pm | Anna Holsgrove on site Andrew Knight, Hazel Colquhoun on site pm FULL TEAM SITE MEETING 4pm | Felice arrives in Hull + 1 assistant, projection/stencilling overnight FULL TEAM SITE MEETING 4pm
| Thursday | 21 | Setworks on site, fourth towers delivered 8am, third towers erected | Marie Bak Mortensen on site Hazel Colquhoun on site until 2pm | 2nd assistant arrives Painting assistants on site (?) Painting during day, projection/stencilling overnight | Pezo and Sofia arrive Hull
| Friday | 22 | Setworks on site, fourth towers erected by end of day | Marie Bak Mortensen on site Hazel Colquhoun on site am | Painting assistants on site Painting during day, projection/stencilling overnight Press briefing and artist/architect photography | Artist/architect photography, opportunity for interviews
| Saturday | 23 | Setworks leave site, barrers remain for artwork completion | Sam Wilkinson on site Anna Holsgrove from 17:45pm | 2 Felice assistants on site. Painting assistants on site Poss projection/stencilling overnight Painting during day,
| Sunday | 24 |  | Anna Holsgrove on site until 6pm | 2 Felice assistants on site. Painting assistants on site Painting during day Felice leaves 12:00
| Monday | 25 |  | Hazel Colquhoun, Andrew Knight on site Anna Holsgrove, Marie Bak Mortensen from 1pm | 2 Felice assistants on site. Painting assistants on site Painting during day, | Sofia and Pezo available for interviews |  | 4pm at Hull Minster Soft launch/drinks prior to TP preview
| Tuesday | 26 |  | Hazel Colquhoun, Andrew Knight on site | 2 Felice assistants on site. Painting assistants on site Painting during day | Sofia and Pezo leave Hull (am) Talk at the RIBA, London 19:00
| Wednesday | 27 |  | Hazel Colquhoun, Andrew Knight on site | 2 Felice assistants on site. Painting assistants on site Painting during day 1 Felice assistant leaves 12:30 | Flying out from London
| Thursday | 28 |  |  | 1 Felice assistants on site until 15:30 |  |  | Installation photography (pm) ?
| Friday | 29 | [5 empty] | Issue photography?
| Saturday | 30
October | Sunday | 1 | [5 empty] | Open to public
| Monday | 2 | [5 empty] | OFFICIAL SEASON 4 LAUNCH 6.30 pm, Market Halls Trinity Sq
| Tuesday | 3
| Wednesday | 4
| Thursday | 5
| Friday | 6 |  |  |  |  | TBC: Opera ( Spring 2017 - Autumn 2017) CH
| Saturday | 7
| Sunday | 8
| Monday | 9
| Tuesday | 10
| Wednesday | 11
| Thursday | 12
| Friday | 13
| Saturday | 14
Contacts | Hazel Colquhoun |  | H2017 curator | 07970 664712
| Sam Wilkinson |  | H2017 curator | 07917 153555
| Andrew Knight |  | H2017 curator | 07801 260503
| Laura Beddows |  | H2017 Asst producer | 07968 855187
| Liam Rich |  | H2017 Producer | 07957 193195.
| Sam Hunt |  | H2017 Exec Producer | 0796 8855187
| Marie Bak Mortensen |  | RIBA | 07501 466646
| Anna Holsgrove |  | RIBA | 07814 306 379
| Tim Meaker |  | Setworks | 07775 896690