|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ARTIST** | **CONTACT** | **OUTLINE** | **AREA** | **KEY DATES** | **TO DO** |
| **Joshua Sofaer** | joshua@joshuasofaer.com<http://www.joshuasofaer.com/> | Nose Emporium  | Bransholme North Point Shopping Centre – Louise Smith  | 27/28 July site visit28 – 30 August get in31-4 Sept – Live 5 Sept get out | Contract - SignedShop Unit - ConfirmedActor x 2 – Hellen Urben & Delivery of set – Louise SmithTool Box – centre providingMarketing steer – Nose to see you # or 2017?Safeguarding – DBS check to be sent in, policy/guide advice to be givenRisk Ass & PL to be sent to centreSet design plan |
| **Periplum****Claire Raftery****Damian Wright** | periplumperformance@googlemail.com<http://www.periplum.co.uk> | Message in a Bottle | East / North | Early July –Site visitMid July – 1st community workshopLate July 2nd community workshopEarly August – 3rd community workshopMid/late august 7 day residency  | Site visit 12 July Awaiting date for first visit – 9th July PossiblyGetting delivery options & contacts – Milk float ongoingList of east & north groups – Site visit to Preston Road & Greatfield |
| **Davy & Kristin McGuire** | davyandkristinmcguire@gmail.com<http://www.davyandkristinmcguire.com> | Little Film Scenes  | North/WestBingo Hall & Anlaby Rd | 7 – 12th Sept Live | Hire car – extra info required by foxy – EB to get other care hire contact for LOGG artistsLocation advice – Anlaby Road, outside of bingo hall and doorway for 2016 possibly inside for 2017Permissions for bingo hallOther site along Anlaby Rd to be identified Story board |