## Summary
Artist | Accomod. booked | Budget confirmed | Budget totals | DBS received | PLI received | Dates confirmed | Contract sent | Contract signed | PO sent | 1st invoice | Locations confirmed | Volunteer requirements | Event framework sent | 2nd invoice | 3rd invoice | M&E update
Davy & Kristin McGuire | 2016-06-21 | 2016-07-05 | 18658.5 | N/A | 2016-07-31 | 2016-06-29 | 2016-06-27 | 2016-07-05 | 2016-07-11 | 2016-07-11 | 2016-07-05 | 10-11 Sept. 7:15-11:30pm | 2016-09-01 | 2016-09-09 |  | 2016-11-07
Aswarm | 2016-08-04 | 2016-07-14 | 18831 | 2016-09-05 | 2016-08-22 | 2016-07-15 | 2016-06-29 | 2016-08-08 | 2016-08-10 | 2016-08-11 | 2016-05-20 | 28 Sept - 2 Oct various times | 2016-08-28 | 2016-09-20
Periplum | 2016-08-05 | 2016-07-14 | 17687 | 2016-08-08 | 2016-08-17 | 2016-08-18 | 2016-06-29 | 2016-07-14 | 2016-07-22 | 2016-07-22 | 2016-08-03 | None | 18 Aug draft | 2016-09-30 | 2016-09-30 | 2016-11-03
Scottee | 2016-07-25 | 2016-07-14 | 19486.57 | 2016-09-01 | 2016-08-03 | 2016-07-06 | 2016-06-23 | 2016-08-08 | 2016-08-08 | 2016-08-10 | 2016-08-08 | None | 2016-08-29 | 2016-08-16
Joshua Sofaer | 2016-06-27 | 2016-06-10 | 18933.72 | 2016-07-05 | 2016-07-05 | 2016-06-27 | 2016-06-23 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-08 | 28-30 Aug: 2 to install set. 31-4 Sept 2 to welcome, 5th to help break down | 2016-07-21 | 2016-07-22 | 2016-09-05 | 2016-10-17
Dominic Wilcox | 2016-08-18 | 2016-07-14 | 18130 | Seen by Adam | 2016-08-11 | 2016-08-18 | 2016-06-29 | 2016-08-23 | 2016-09-02 | 2016-11-07 | 2016-07-28 | None | 9 Aug draft | 2016-11-07 | 2016-11-07
Lone Twin | 2016-07-29 | 2016-07-14 | 18973.2 | Never received | 2016-08-23 | 2016-07-29 | 2016-06-29 | 2016-07-25 | 2016-08-01 | 2016-07-29 | 2016-07-06 | 3-10 Sept: 2 volunteers per day | 2016-08-26 | 20 Sept approved
|  | commission budget total | 130699.99
|  | Venue (contingency) | 9300.01
|  | Overall budget total | 140000

## LONE TWIN
LOGG 2016 ARTIST | LONE TWIN
Area of Hull | Longhill
Site Visit/s dates/times | 4th August
Workshop/other dates/times | n/a
Delivery dates/Times | 3-11 September (get in 30 Aug - 2 Sept, culmination 11th Sept)
Budget agreed | Yes
Invoice received | see summary
Contract signed | yes
Highlighted to ESAG | on August 11th
Framework doc agreed | Template sent
Concept/Creative matters
Locations used | St Margaret's Welcome Centre and East Mount Community Centre (as working hub)
Licensing/TEN | N/A
Permissions/Consent | They do ask participants to sign a waiver in advance regarding recording
PRS / PPL required | n/a
Venue agreement | East Mount Community Centre as a project hub. Venue agreement required between artist and venue?
H & S matters | Unaccompanied performer in a suit - is it breatheable? Audio equipment within suit hazardous? Will tripping hazards be visible to the performer from within the suit?
Enviro Health matters | n/a
Staffing matters | will the Visitor be accompanied at all times? Yes, by local community member and/or another member of LT
Volunteer request | request for 2 local volunteers in case local knowledge required. Sue Nicholson is a Pioneer from Longhill - 07834727438 - confirmed availability
Volunteer needs | Potentially pack lunches and coffee/tea/water/biscuits. Break space can be located in community space with artists
Security matters | Exhibition space need to be invigilated? - member of LT team will be there at all times
Equipment matters | Suit, recording device, exhibition materials and space, etc.
Power/light/matters | self-contained costume. Will they need support in the community centre?
Access matters | aiming to include disabled person as participant with Visitor
Access Guide sent | Sent 26 July
Safeguarding matters | for recording, waiver required. Visitor is never alone with a child. Protocols in place. Have determined balance of organised vs random schedule. All LT performers are DBS checked
DBS docs checked | Confirmed but awaiting proof from GVS
Environmental matters | N/A
Audience control matters | N/A - the Visitor will be shadowing one person/family at a time. Potential exhibition space will unlikely be highly crowded as the locations are low-key.
Emergency concerns | None
Insurance checked | Not yet.
Timeline okay | Yes
RA's checked | not yet
Marketing matters | No marketing required, but LT may create a low fi lost cat-style poster to scatter round Longhill
M & E notes | Artists will be documenting using sound recording, video and photography all resulting in an exhibition. Ie the project itself is a form of evaluation.
Blog started by artist | Not yet.
Other detail required
Shared Artists Unit | Not required by the company
Key contacts for project | Karen Okra link with Longhill, Trisha (St Margaret's Welcome Centre), Diane (Eastmount Centre)
Production Manager notes | H&S/safeguarding issues need sorting re: suit, loneworking, voice recording, etc. , paperwork, comms (us), venue permissions, exhibition install, volunteers.

## SCOTTEE
LOGG 2016 ARTIST | SCOTTEE
Area of Hull | East, 362 Holderness Road (subject to venue agreement)
Site Visit/s dates/times | 1st completed - 2nd due on 15+16 August
Workshop/other dates/times | N/A
Delivery dates/times | 2-3 September 11-4pm (1st: get in, 4th: get out)
Budget agreed | yes
Invoice received | first invoice paid, second invoice received.
Contract signed | Molly has signed
Highlighted to ESAG | on August 11th
Framework doc agreed | Draft received from Anya
Concept/Creative matters | Balancing the LOGG and Gay agenda? Is there magic/curiousity ...and provocation? Need to see designs asap
Locations used | 362 Holderness Road
Licensing/TEN | Required - Anya applied
Permissions/Consent | Venue agreement with letting agent for perusal
PRS / PPL required | Need to establish if required
Venue agreement | Venue agreement with letting agent for perusal. Is some kind of indemnity insurance required?
H & S matters | Small, in decent condition with all facilities in place. Some electrical items and furniture is in the space and will need stacking and removing.
Enviro Health matters | Refreshments offered to public, so EH to be informed via ESAG and TEN
Staffing matters | Provided by Scottee team
Volunteer request | None requested
Volunteer needs | N/A
Security matters | Will be present but invisible during performance times
Equipment matters | We need to see a layout or designs for inside the unit.
Power/light/matters | Artist supplies lighting. Power is available in the unit.
Access matters | Decent access as per normal shop/office on the ground floor.
Access Guide sent | Sent out 26 July
Safeguarding matters | Policy required with regards children accessing the space. Age limits/accompanied. DBS unlikely. Signage required.
DBS docs checked | N/A
Environmental matters | None.
Audience control matters | How will they manage crowds outside, assuming it's popular?
Emergency concerns | Will need evac plan from shop unit - agree max number in the space at any one time.
Insurance checked | yes
Timeline okay | yes
RA's checked | Not yet
Marketing matters | This project needs marketing to achieve the numbers they're aiming for. Marketing Plan requested
M & E notes | There will need to be some sort of documentation probably from our team.
Blog started by artist | Not yet.
Other detail required
Shared Artists Unit | Not requested
Key contacts for project | Leonards Letting Agent, Andy Train, Chris Collumb from Fuel, Pride planning committee, etc, local queens: Beyonce, Miss Behave, Miss Courtney Shortney, Liva Birds, Gloria Hole and Potato (more TBC)
Production Manager notes | Coordination with Scottee PM.

## DOMINIC
LOGG 2016 ARTIST | DOMINIC WILCOX
Area of Hull | Boothferry/Gypsyville/Walton Street
Site Visit/s dates/times | 1st completed
Workshop/other dates/times | 25 - 29 September
Delivery dates/times | 25 and 28th September at Walton Street Market
Budget agreed | Reworked for a final time with higher amount
Invoice received | no
Contract signed | Sent to Dominic, awaiting signature
Highlighted to ESAG | on 11 August
Framework doc agreed | not yet
Concept/Creative matters | Experienced improvisors required for performances at market & schoools - have been sourced
Locations used | Walton Street Market. Primary schools in the west, Rokeby Primary confirmed, but seem flexible - Francis Askew-26th September - Wheeler Primary-all confirmed
Licensing/TEN | Not required
Permissions/Consent | Walton St Market have agreed to host stall without charge
PRS / PPL required | n/a
H & S matters | Working with metal potentially sharp objects
Enviro Health matters | n/a
Staffing matters | Performers being sourced for performance element
Volunteer request | None.
Volunteer needs | N/A
Security matters | Objects will need to be attended by no security personnel required.
Equipment matters | Market stall being built by Dominic with guidance from performers
Power/light/matters | None. Power for microphones (performance) to be low voltage if required.
Access matters | None given the sites. May bring stall to groups such as Age UK and maybe another
Access Guide sent | Yes
Safeguarding matters | Working within schools
DBS docs checked | Check DBS
Environmental matters | Waste management of items made - what happens to items after project? Who owns the objects?!
Audience control matters | May need to control if becomes very popular within market setting.
Emergency concerns | Will follow market evacuation procedures
Insurance checked | Not yet
Timeline okay | Awaiting confirmation from schools, venue and performers
RA's checked | Not yet
Marketing matters | Not required. Dominic may put up 'Lost & Found' posters nearby with a number to call. He wants to film/photo performances.
M & E notes | Will need to keep a record of participants
Blog started by artist | Imminently.
Other detail required | Performers to be sourced for improvised show in late September
Shared Artists Unit | Requested
Key contacts for project | Roisha (Francis Askew, Rokeby and Wheeler Primaries) Steve Hess (Walton St market), Men in Sheds, Age UK
Production Manager notes | Confirm schools workshop dates, shared artists unit and perhaps assist Dominic with the market stall delivery? Paperwork - will most likely need assistance in writing risk assessments, etc.

## THOR
LOGG 2016 ARTIST | THOR / ASWARM
Area of Hull | Beverley Road and bus routes off
Site Visit/s dates/times | 1st completed
Workshop/other dates/times | 1st workshop complete. Returning early August (TBC) to record voices.
Delivery dates/times | 8-12 September pop-up phone booths activity. 28 Sept-2 Oct for bus stop installation.
Budget agreed | yes
Invoice received | first received and paid
Contract signed | yes
Highlighted to ESAG | on 11 August
Framework doc agreed | Template sent
Concept/Creative matters
Locations used | Bus stop on Beverley Road. Other locations for phone booth agreed
Licensing/TEN | N/A
Permissions/Consent | Req from JC Decaux (confirmed), Council streetscene (confirmed) - Kerry warmed up Ian from JCDecaux, Dave warmed up Andy W from KWL . Also Asda being chased by Adam. Also locations for 'pop up' phone booth chased by Thor and Adam.
PRS / PPL required | n/a
H & S matters | Woodburner, hanging speakers, distractions from driving, crowds gathering,
Enviro Health matters | Offering free mint tea to audience
Staffing matters
Volunteer request | Requested - but need to confirm role as it is limited under Hull 2017 rules
Volunteer needs | Pack lunches, coffee, tea, water and biscuits. Will need a break area, being sourced by Adam at Asda community room.
Security matters | overnight security to look after site and evening security for safety of staff, as advised by ESAG
Equipment matters
Power/light/matters | self-contained power, lighting, etc - probably 12v
Access matters
Access Guide sent | sent 27 July
Safeguarding matters | Awareness required given the public nature of site
DBS docs checked | n/a
Environmental matters
Audience control matters | This project largely reliant on passing audience but some awareness raising required with groups/individuals involved in source material
Emergency concerns
Insurance checked
Timeline okay
RA's checked
Marketing matters | Would be good to have a hashtag visible on bus stop and phone box
M & E notes
Blog started by artist | Imminently
Other detail required
Shared Artists Unit | Requested
Key contacts for project | Council: Kerry Ryan (public transport), Graham Lownsborough (works), Dave Baines (street lights). JCDecaux: Ian. Poetry: Rob Bell.
Production Manager notes | Finalise permissions from all partners (see above), coordinate all paperwork and perhaps be on hand for install. Identify locations for phonebox, may need overnight security organising. Also volunteer needs not yet identified.

## JOSHUA
LOGG 2016 ARTIST | JOSHUA
Area of Hull | North - North Point Shopping Centre
Site Visit/s dates/times | completed.
Workshop/other dates/times | N/A
Delivery dates/times | 27 Aug - 5 September (live 31-4)
Budget agreed | Yes
Invoice received | received and paid first two invoices
Contract signed | Yes
Highlighted to ESAG | on August 11th
Framework doc agreed | yes
Concept/Creative matters | Designs received
Locations used | shop unit in North Point Shopping Centre, Bransholme
Licensing/TEN | Covered by shopping centre licence
Permissions/Consent | Venue agreement required. Consent form in development
PRS / PPL required | Covered by NPSC
H & S matters | A cast of your nose (using the alginate that dentists use to make impressions of your teeth). It takes about 2 hours in total.Waiver required (in a creative way) regarding possible allergic reaction, etc.
Enviro Health matters | A thermoformed plastic version of the nose is made from the cast, water is used and plastic residues are left in the water - the water will be sived, plastic discarded into recycling and water dispossed in outside grate
Staffing matters | Sorted by Joshua, Adam, Elizabeth and Lou to check in every now and then
Volunteer request | Requested
Volunteer needs | Pack lunches, coffee, tea, water and biscuits. Break area can be located in the back of the shop.
Security matters | n/a (because within North Point Shopping Centre)
Equipment matters | Thermoforming machine gets hot, this will be set up behind a screen with a windo in so public can see but not touch the equipment (see design)
Power/light/matters | North Point covering costs
Access matters | Centre and unit accessible to customers
Access Guide sent | sent 27 July. May invite groups via James McGuire
Safeguarding matters | Detailed plan required as there is phyical touching. Age limit and/or adult/parent accompaniment arrangement to be agreed. Background checks on staff (Joshua has DBS - but to be checked)
DBS docs checked | Required from all staff - Joshua check is form Scotland?
Environmental matters | Water to be sieved before emptied in outside grate
Audience control matters | booking system if it gets busy
Emergency concerns | Most of these will be in consultation with the shopping centre with their own Emergency arrangements
Insurance checked
Timeline okay
RA's checked
Marketing matters | Twitter & Instagram used by the artist
M & E notes
Blog started by artist
Other detail required
Shared Artists Unit | Not requested
Key contacts for project | Shopping Centre: Louise Smith
Production Manager notes | Coordinate paperwork: insurance, DBS, Ras, venue permissions, etc. Note: most of this is already done. Volunteer needs not yet addressed.

## D & K
LOGG 2016 ARTIST | DAVY & KRISTEN
Area of Hull | West - Carlton Bingo Hall, Anlaby Road
Site Visit/s/times | completed but will need another one for Adam
Workshop/other dates/times | n/a
Delivery dates/times | 8th & 9th get in 10th & 11th Live 12th Get out
Budget agreed | yes
Invoice received | first invoice paid
Contract signed | yes
Highlighted to ESAG | 2016-08-11
Framework doc agreed | not yet received
Concept/Creative matters | Development of 4 scenes - still need to received updated story
Locations used | Carlton Anlaby Road
Licensing/TEN | no
Permissions/Consent | From Carlton - Sonny Nagra. Not yet confirmed.
PRS / PPL required
H & S matters | Artists workign in the derolict building / Traffic on Anlaby road / Show at night
Enviro Health matters | Building / lighting & Sound
Staffing matters
Volunteer request | Yes - requested
Volunteer needs | Will require a break area with tea, coffee, water and biscuits, potentially in a private room of a pub
Security matters | Will need security
Equipment matters | Artist may need truss - already discussed between Adam and Davy
Power/light/matters | Building has no electric. Needs generator but issues with owner if it is located inside the building?
Access matters
Access Guide sent | sent 27 July
Safeguarding matters | N/A
DBS docs checked | N/A
Environmental matters | Disruption to pigeons and other creatures such as bats roosting in the building
Audience control matters | Close to the road, distraction to drivers, people crowding to see small work.
Emergency concerns | Road accidents. Crowd issues? Who is in charge if there is an emergency? Who stops the installation and moves the audience, etc?
Insurance checked | Received.
Timeline okay | Issue: confirming content
RA's checked | not yet completed.
Marketing matters | Going to be a popup show. We either need to wait for people to see something and then respond, or we need to advertise it ahead and/or invite audiences to come see. Eg can we invite newspapers to the first night and they can lead on spreading stories…
M & E notes | Need to monitor how many people are seeing the work.
Blog started by artist | Not yet
Other detail required | No.
Shared Artists Unit | Not requested
Key contacts for project | Carlton Bingo - Sonny Nagra and Shaun Larvin
Production Manager notes | Awaiting confirmation of content for scenes, which will determine production needs. For example, potential to animate window from inside the building. Other installations will be projected using pico projectors (i.e. battery operated). Confirmation of permission to use site still work in progress.
Need for security/stewarding? Install, volunteers, paperwork.

## PERIPLUM
LOGG 2016 ARTIST | PERIPLUM
Area of Hull | Greatfield Estate and Preston Road (east)
Site Visit/s dates/times | completed
Workshop/other dates/times | 11 August TBC at Child Dynamix at St Stephen's and 20-28th August 1 day to be agreed with Child Dynamix and Purple House
Delivery dates/times | 23-25 Sept and 29-2 Oct
Budget agreed | yes
Invoice received | see summary
Contract signed | yes
Highlighted to ESAG | On the 11th August
Framework doc agreed | Sent Awaiting details to fill out
Concept/Creative matters | Design for bottle yet to be received. Vehicle for deliveries confirmed.
Locations used | Greatfield Estate and Preston Road for deliveries. For workshops: Child Dynamix, St Stephens and Purple House
Licensing/TEN | Yes
Permissions/Consent | Informed Jane Price of area teams. Will need permission from venues displaying bottles once identified.
PRS / PPL required | N/A all original compositions
H & S matters | Glass bottles. Horse and cart.
Enviro Health matters | Disposal of bottles and horse manure ie waste management
Staffing matters | Someone to deliver bottles, perhaps owner of vehicle?
Volunteer request | N/A
Volunteer needs | N/A
Security matters
Equipment matters | horse and cart
Power/light/matters | Potentially for displays.
Access matters | Will be slightly unaware of access issues for those receiving bottles because we won't know who receives them or not.
Access Guide sent | Yes.
Safeguarding matters | Workshop participants. Bottle recipients could be targeted in an improper way - how can we analyse the way in which participants are selected by the community.
DBS docs checked | N/A
Environmental matters | N/A
Audience control matters | N/A
Emergency concerns | None.
Insurance checked | Received
Timeline okay | Not yet confirmed.
RA's checked | no
Marketing matters | Depends on when it happens. We don't want any marketing leading up, but we will need to have a response once the bottles start getting delivered.
M & E notes | Periplum to keep a log of who the bottles have been sent to, and the process of nominating participants.
Blog started by artist | Not yet
Other detail required | No.
Shared Artists Unit | Probably for bottles and other supplies such as treasure chests.
Key contacts for project | Jenny Mason of St. Stephens, Paul Clark and Jane Stafford of Child Dynamix. Christina Reading of Purple House and Claire Taylor of Greatfield Hub.
Production Manager notes | Awaiting schedule of deliveries and time between delivering, collection and delivery to named individuals. Awaiting confirmation of milk float, and workshop times. Also confirm treasure chest trail locations (Louise?)