## Summary (hidden)
Tab name: | 1 |  | Tab name: | Tab name: | Tab name:
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!

## Timeline
[7 empty] | NOV |  | DEC |  |  |  | JAN |  |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC
ITEM | START | END | time axis 2016-10-24 to 2018-01-01
KEY MILESTONES | bar: 2016-10-24 to 2018-01-01
Initial Public Announcement | 2017-04-29 | 2017-04-29 | bar: 2016-10-24 to 2018-01-01
On Sale Date - All Tickets | 2017-05-02 | 2017-05-02 | bar: 2016-10-24 to 2018-01-01
Performance week | 2017-05-30 | 2017-06-04 | bar: 2016-10-24 to 2018-01-01
Get In & Get Out dates | 2017-05-29 | 2017-06-04 | bar: 2016-10-24 to 2018-01-01
|  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
|  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
|  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
|  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
PROGRAMMING
Programme finalised
VENUE
Catering confirmed
Staffing confirmed
ADMINISTRATION
Programming Consultant (music) contracted
Deal Memo & Contracting | 2017-04-03 | bar: 2016-10-24 to 2018-01-01
Copy and images to Marketing/Digital | 2017-04-13 | 2017-04-13
Ticketing Set Up Requests | 2017-04-10 | 2017-04-15 | bar: 2017-03-27 to 2017-04-03
New supplier forms issued and returned to finance
POs raised for visiting companies
Volunteer requests submitted (including evaluation???) | 2017-04-07 | 2017-04-12 | bar: 2016-10-24 to 2018-01-01
Volunteer training day | 2017-04-27 | 2017-04-28 | bar: 2016-10-24 to 2018-01-01
FOH Co-ordinator & Event Manager Schedules Completed
FOH Coordinators & Event Managers Contracted
FOH Coordinators & Event Managers Briefing
|  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
MAR COMMS DIGITAL | bar: 2016-10-24 to 2018-01-01
Mar Comms Plan - High Level | bar: 2016-10-24 to 2018-01-01
Mar Comms Plan - Detailed | bar: 2016-10-24 to 2018-01-01
Festival Brochure signed off | bar: 2016-10-24 to 2018-01-01
Festival Brochure delivered | bar: 2016-10-24 to 2018-01-01
Marketing Engagement Leads contracted | bar: 2016-10-24 to 2018-01-01
Photographer/Filming Planned | bar: 2016-10-24 to 2018-01-01
Venue dressing finalised | bar: 2016-10-24 to 2018-01-01
|  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
PRODUCTION (TECH & OPS) | bar: 2016-10-24 to 2018-01-01
Initial site visits | 2017-03-10 | bar: 2016-10-24 to 2018-01-01
HPSS Quote Finalised | 2017-04-04 | 2017-04-28 | bar: 2016-10-24 to 2018-01-01
Security booked |  | 2017-05-12
First Aid booked |  | 2017-05-12 | bar: 2016-10-24 to 2018-01-01
All Occassions (barriers) Ordered |  | 2017-04-28
Event Management Plan Draft 1 | 2017-04-04 | 2017-04-11
Final Event Management Plan | 2017-04-14 | 2017-05-11
ESAG Meeting 1 | N/A | 2017-04-13
ESAG Meeting 2 | N/A | 2017-05-11
TEN Licences submitted | N/A | 2017-04-21
Accreditation List handed to MM | 2017-05-01 | 2017-05-12
Festival comms plan finalised | 2017-05-01 | 2017-05-08
Production Schedule Finalised | 2017-04-05 | 2017-05-19
Support logistics schedule finalised | 2017-04-05 | 2017-05-19
Absolute Final Date for T.E.N.s (not late) | N/A | 2017-05-15
VENUE MANAGERS MEETINGS | bar: 2016-10-24 to 2018-01-01
May 1st Meeting | bar: 2016-10-24 to 2018-01-01
May 2nd Meeting
June | bar: 2016-10-24 to 2018-01-01
July
September
October
November
December
EVALUATION
Delivery details agreed
Logistics confirmed with Production