## Overview
Site Visit Dates | Workshops | Get In | Delivery Dates | Get Out | Artist | Location
2016-07-05 | N/A | 27-29 Aug | 30 Aug - 4 Sept | 5-6 Sept | Joshua Sofaer | North Point Shopping Centre
3-6 July | N/A | 8-9 Sept | 10-11 Sept | 2016-09-12 | Davy & Kristin McGuire | Anlaby Road
11-13 July | 2016-07-12 |  | 24 - 28 Aug |  | Thor Hack 2 | Beverley Road
| 2016-07-13 |  | 9 - 12 Sept |  | Thor Hack 1 | Boulevard
w/c 18 July | N/A | 1-4 Sept. | 5 - 11 Sept | 11 Sept. | Lone Twin | Longhill Estate
2016-07-11 | N/A | 2016-09-01 | 2-3 Sep | 2016-09-04 | Scottee | Greenwood Ave
11-12 July | Mid-July; Late-July & Early Aug | N/A | Mid-late August | late Aug | Periplum | Ings/Sutton/East Park
13-19 July | 20 Aug - 4 sept |  | 20 Aug - 4 Sept | 2016-09-05 | Dominic Wilcox | Gipsyville/Boothferry Estate

## GANTT
Week of | 2016-07-04 | 2016-07-11 | 2016-07-18 | 2016-07-25 | 2016-08-01 | 2016-08-08 | 2016-08-15 | 2016-08-22 | 2016-08-29 | 2016-09-04 | 2016-09-11
Davy & Kristin McGuire | 2016-07-04: Site visit (3-6); 2016-09-04: Get in (7-8); 2016-09-11: Hullywood (10-12)
Aswarm | 2016-07-11: Site visit (11-13), workshops (12&13); 2016-08-22: Hack 2 (24-28); 2016-09-04: Hack 1 (9-12)
Periplum | 2016-07-04: Site visit (11-12); 2016-07-11: First workshop; 2016-07-25: Second workshop; 2016-08-01: Third workshop; 2016-08-15: Residency
Scottee | 2016-07-11: Site visit (11), Pride (16); 2016-08-15: Site visit (15-16); 2016-08-29: Get in (1), The Door (2-3); 2016-09-04: Get out (4)
Joshua Sofaer | 2016-07-04: Site visit (6); 2016-08-22: Get in (27-30); 2016-08-29: Nose to Meet You (31-4); 2016-09-04: Get out (5)
Dominic Wilcox | 2016-07-11: Site visit (13-19); 2016-08-15: 20th August - 4th September Delivery and workshops
Lone Twin | 2016-07-18: Site visit; 2016-08-29: Get in (1-4); 2016-09-04: The Visitor (5-11)

## Checklist
Artist | Accomod. booked | Budget confirmed | Budget totals | PLI received | Dates confirmed | Contract sent | Contract signed | PO sent | 1st invoice | Locations confirmed | Volunteer requirements | Update report sent | 2nd invoice | 3rd invoice
Davy & Kristin McGuire | 2016-06-21 | 2016-07-05 | 18658.5 |  | 2016-06-29 | 2016-06-27 | 2016-07-05 | 2016-07-11 | 2016-07-11 | 2016-07-05 | 8 volunteers 9-12 Sept. 7:30-11:30pm
Aswarm | 6 July (site visit only) | 2016-07-14 | 18831 |  |  | 2016-06-29 |  |  |  | 2016-05-20 | 24-28 Aug & 9-12 Sept 2 volunteers each day
Periplum | 11 July (site visit only) | 2016-07-14 | 17687 |  |  | 2016-06-29 | 2016-07-14 | 2016-07-22 | 2016-07-22 |  | TBD
Scottee | 2016-07-25 | 2016-07-14 | 19486.57 |  | 2016-07-06 | 2016-06-23 | 2016-07-20 |  |  |  | None
Joshua Sofaer | 2016-06-27 | 2016-06-10 | 18933.72 | 2016-07-05 | 2016-06-27 | 2016-06-23 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-08 | 28-30 Aug: 1 to install set. 31-5 Sept 2 to welcome | 2016-07-21 | 2016-07-22
Dominic Wilcox |  | 2016-07-14 | 17260 |  |  | 2016-06-29 |  |  |  |  | TBD
Lone Twin | 2016-07-29 | 2016-07-14 | 18973.2 |  |  | 2016-06-29 | 2016-07-25 | 2016-08-01 | 2016-07-29 | 2016-07-06 | 1-11 Sept: 2 volunteers per day
total |  |  | 129829.99
Venue (contingency) |  |  | 10170.01
140000