## Guidance
ABOUT PROJECT RISK REGISTERS
Every project we have any responsibility for delivering should have a project risk register - it is a useful tool to ensure important things have been considered and safeguards put in place wherever possible. It is a live planning & monitoring tool, to be updated and added to regularly.
The Executive Producer owns the risk register, with Producer, Assistant Producer and third parties contributing.
Third parties cannot own the risk register: there are some risks we cannot devolve (most obviously the risk that the third party will not deliver), and we remain responsible even for those we can. Completing a risk register will help ensure nothing falls between the gaps of in-house and third party delivery. You may want to ask the third party to develop the risk register, add your own risks, then keep it up-to-date via your usual communications & updates with them.
The project team should review the risk register regularly. You might, for example, review all the residual red risks at one meeting, the ambers at the next etc…
If a risk needs to be escalated, it should be raised via an Executive Producer at Tuesday Programming.
NB Project risk registers are different to event risk assessments. Event risk assessments are about preventing harm during a fixed period of activity, and completed by the Tech & Ops team. Project risk registers are about foreseeing and preventing obstacles to your project.
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | eg well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | eg thorough planning, reliable quotes
Decision making causes delays | Additional pressure on internal project team | eg foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | eg full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | eg early involvement of Legal team, use of standard templates
Failure to engage creative team | Inability to deliver project
Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | eg early setting up of suppliers on system, correct use of POs, management of expectations
Failure to secure appropriate venue | Inability to deliver project | eg early discussions, backup plans
Failure to secure necessary permissions or licences | Inability to delivery project | eg early involvement of Tech & Ops team, appropriate slot at ESAG
Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | eg thorough planning
Insufficient budget | Inability to deliver project | eg accurate forecasts, management of expectations
Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | eg early involvement of Legal team
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | eg roles & responsibilities defined, regular use of Artifax inc milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | eg clear roles & responsibilities, contracts where required, regular updates
Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | eg early involvement of Tech & Ops team
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | eg agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | eg reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | eg clearly defined project scope, clear process for managing change
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | eg making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | eg thorough agreements/contracts
Weather or natural environment | Inability to deliver project as intended | eg weatherproofing, indoor alternatives

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | Sam Hunt, Jo Nockels (ON), Dominic (ON), Martin A, artists involved in the creation of the performance. | 3 | 5 | 15 | Have been working closely with the team, attending visits to the bridge and capturing elements of their work. Having constructive discussions if visions do look like they are shfting at all. | 2 | 3 | 6 | Open
2 | Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | Martin A, Jo and Dom (ON) | 2 | 2 | 4 | Have carefully constructed the budget with ON and contract requires budget updates before the next stages of payment. Also with constant communication we are able to assess where spend might be becoming difficult in places. | 2 | 3 | 6 | Open
3 | Decision making causes delays | Additional pressure on internal project team | Jo Nockels (ON), Martin A, Sam H | 1 | 3 | 3 | Decisions are being made quickly with the creative and production team established early on and an incredible working relationship with the bridge. | 2 | 4 | 8 | Open
4 | Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | Martin A, Jo and Dom (ON) | 0 | 5 | 0 | Project sold out very quickly. Looking to increase number of performances. |  |  | 0
5 | Failure to contract all parties effectively | Inability to deliver project | Martin A, Sam H | 0 | 5 | 0 | All parties have been contracted to effective milestones. Contract signed off my legal. |  |  | 0
6 | Failure to engage creative team | Inability to deliver project | Opera North | 0 | 5 | 0 | Creative team fully engaged. |  |  | 0
7 | Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | Martin A | 3 | 2 | 6 | Awaiting feedback to payment requirements in terms of reporting. Confident this will arrive in due course. | 3 | 1 | 3
8 | Failure to secure appropriate venue | Inability to deliver project | Opera North | 2 | 2 | 4 | Venue secured, work happening to tidy it up. |  |  | 0
9 | Failure to secure necessary permissions or licences | Inability to delivery project | ON | 0 | 0 | 0 | All permissions have been sought from bridge board and ON and Martin A are seeing East Riding Council to make sure wayfinding is all ok to the site from station. |  |  | 0
10 | Accidents on the bridge from anyone taking part | Injury caused to participants | ON/Hull2017 and Humber Bridge Board | 1 | 4 | 4 | The Humber bridge have telephones dotted all along the bridge where people can call for assistance. The number for the TIC will also be on literature in case of an emergency. First aid trained staff at TIC and working on bridge to attend any emergency. | 1 | 4 | 4
11 | Headsets stolen/broken | Running out of headsets for those who have booked. | ON/Martin A/Sam Hunt | 3 | 5 | 15 | Details taken of every booking and reminded to bring them back. This is starting on a trust basis - if too many headsets go missing then we will implement a deposit scheme and notify participants before they arrive. | 2 | 4 | 8
12 | Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | ON | 2 | 5 | 10 | ON insuring the project as they deliver it. Obtained and checked over insurance policies for this. All seem to be adequate to cover risks identified. | 1 | 5 | 5
13 | Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | ON/Sam Hunt/ Martin A | 2 | 4 | 8 | Working monitored closely and all milstones have been hit with adequate production and creative team. Extra Event manager resource will be implemented after opening weekend to manage headsets and vols. | 1 | 4 | 4
14 | Partners fail to support/deliver as expected | Additional pressure on internal project team | ON/Sam Hunt/ Martin A | 2 | 4 | 8 | Martin has been working closely with Producer's and Production team, as well as the team at the Tourist Information Centre. Initial issues have been troubleshot to find solutions where cover isn't there throughout the month. One example is the battery life of transmitters, better batteries have been bought to ensure they won't require maintenance. | 1 | 3 | 3
15 | Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | Martin A/Sam H/Opera North | 0 | 4 | 0 | Followed all procurment processes internally on this project. | 1 | 1 | 1
16 | Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | Martin A/Dom & Jo ON | 2 | 4 | 8 | Dvolved delivery means that ON have ownership of most project files. The guest booking over the month needs to be clearly established between both parties and this is being done by Producer's from both sides. | 2 | 3 | 6
17 | Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | Martin A/Sam Hunt/ ON | 2 | 4 | 8 | Specific volunteer training is happening for this project with Production Manager and Hull 2017 vounteer team. An event manager will also be present who will manage vols and call in any issues to production team and Hull 2017 team. Production team will be present on opening weekend with vols. Technical support has been purchased the run of the perofrmance from MY Orpheo. | 2 | 1 | 2
18 | Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | Martin A/Sam Hunt/ON | 2 | 3 | 6 | This almost happened then we reigned things back on opening weekend. The ON team are very good at making sure they are not overwhleming themselves with activity. | 2 | 3 | 6
19 | Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed |  | 1 | 4 | 4 | This has not been the case throughout. Production Manager and technical assistance has been perfect. The bridge team are supporting every aspect of the project and staff resource. | 1 | 4 | 4
20 | Suppliers fail to deliver | Inability to deliver project |  | 0 | 5 | 0 | All supplies have been delivered in order to make the project work successfully. We have secured 24 hr technical support on the equipment that has been supplied. | 1 | 4 | 4
21 | Weather or natural environment | Inability to deliver project as intended |  | 4 | 5 | 20 | The weather on the Humber Bridge can change instantly. We will be working with the birdge team, EM and vols to make sure that we communicate any adverse conditions. The print has done well to mention so far that people need to wrap up for this and bring sensible clothing and footwear. | 3 | 5 | 15
22 | One side of the bridge being closed for essential maintenance. | Inability to deliver project on that day |  |  |  | 0 |  |  |  | 0
23 | Injury caused by sharing of the path with people and cyclists. | Potential legal action due to inury. |  |  |  | 0 |  |  |  | 0
24 | Box Office failure. | Customers, press, partners, VIPs not being to experience the installation or not having a satisfactory experience. Loss of confidence in Hull 2017 brands & ON brand | Box Office team 2017/Martin A | 5 | 5 | 25 | Unfortunately this has allready happened. No mitigating action. No plans to resolve general box office issues from Hull 2017 side or evaluate the process before this finishes. | 5 | 5 | 25
25 | [5 empty] | 0 |  |  |  | 0
26 | [5 empty] | 0 |  |  |  | 0
27 | [5 empty] | 0 |  |  |  | 0
28 | [5 empty] | 0 |  |  |  | 0
29 | [5 empty] | 0 |  |  |  | 0
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...