## Sheet1
THE LAST BALLAD OF LILLIAN BILOCCA
LAST UPDATED 05.06.17
W/C | ACTIVITY | REHEARSAL SCHEDULE | # | LOCATION | TIMES | TEAM AVAILABILITY | GUILDHALL | NOTES
2017-05-22
2017-05-29 |  | Full creative team visit |  | Hull | Full day
Mon 5 Jun 2017
2017-06-12
2017-06-13
2017-06-14
2017-06-15
2017-06-16 |  | Venue site-visit & walk-around / Research visit |  | Hull | 12pm - overnight | Sarah & Imogen AV. Jon NA during the day
2017-06-17 |  | Community Consultation TBC |  | Holy Apostle TBC | 9am - 12pm | Sarah, Imogen, Jon, Lindsey
2017-06-18
2017-06-19 |  | Deadline for costing lists/requirements / Comm Cast Call Out |  | Hull |  |  |  | TO BE MOVED WITH ADVICE FROM PM
2017-06-20 |  | Casting of Professional Cast Confirmed |  | London |  |  |  | CONFIRMED WITH SF
2017-06-21
2017-06-22
2017-06-23
2017-06-24
2017-06-25
2017-06-26 | [5 empty] | Amanda NA
2017-06-27 | [5 empty] | Amanda NA
2017-06-28 |  | Casting of Professional Cast TBC |  | Manchester/Hull |  | Amanda NA
2017-06-29 | [5 empty] | Amanda NA
2017-06-30 | [5 empty] | Amanda NA
2017-07-01 | [5 empty] | Amanda NA
2017-07-02 | [5 empty] | Amanda NA
2017-07-03 | [5 empty] | Amanda NA / Sarah NA
2017-07-04 |  | Casting of Professional Cast TBC |  |  |  | Amanda NA / Sarah NA
2017-07-05 |  | Casting of Professional Cast TBC |  |  |  | Amanda NA / Sarah NA
2017-07-06 | [5 empty] | Amanda NA / Sarah NA
2017-07-07 | [5 empty] | Amanda NA / Sarah NA / Jon NA
2017-07-08 |  | Community Cast Auditions |  | Hull |  | Sarah NA |  | 3 sessions of 20-25 people
2017-07-09 |  | Community Cast Auditions |  | Hull |  | Sarah NA |  | 3 sessions of 20-25 people
2017-07-10 | [5 empty] | Imogen NA until 22 Aug / Sarah NA
2017-07-11 | [5 empty] | Sarah NA / Imogen NA
2017-07-12 | [5 empty] | Sarah NA / Imogen NA
2017-07-13 | [5 empty] | Sarah NA / Imogen NA
2017-07-14 | [5 empty] | Sarah NA / Imogen NA
2017-07-15 | [5 empty] | Sarah NA / Imogen NA
2017-07-16 | [5 empty] | Sarah NA / Imogen NA
2017-07-17 | [5 empty] | Sarah NA / Imogen NA
2017-07-18 | [5 empty] | Sarah NA / Imogen NA
2017-07-19 | [5 empty] | Sarah NA / Imogen NA
2017-07-20 | [5 empty] | Sarah NA / Imogen NA
2017-07-21 | [5 empty] | Sarah NA / Imogen NA
2017-07-22 | [5 empty] | Sarah NA / Imogen NA
2017-07-23 | [5 empty] | Sarah NA / Imogen NA
2017-07-24 | [5 empty] | Imogen NA
2017-07-25 | [5 empty] | Imogen NA
2017-07-26 | [5 empty] | Imogen NA
2017-07-27 | [5 empty] | Imogen NA
2017-07-28 |  | Final model meeting |  | Hull |  | Imogen NA
2017-07-29 | [5 empty] | Imogen NA
2017-07-30 | [5 empty] | Imogen NA
2017-07-31 | [5 empty] | Imogen NA
2017-08-01 | [5 empty] | Imogen NA
2017-08-02 | [5 empty] | Imogen NA
2017-08-03 | [5 empty] | Imogen NA
2017-08-04 | [5 empty] | Imogen NA
2017-08-05 | Week 1 | Community Cast Rehearsals | 1 | Holy Apostle |  | Imogen NA
2017-08-06 | Week 1 | Community Cast Rehearsals | 1 | Holy Apostle |  | Imogen NA
2017-08-07 | [5 empty] | Imogen NA
2017-08-08 | [5 empty] | Imogen NA
2017-08-09 | [5 empty] | Imogen NA
2017-08-10 | [5 empty] | Imogen NA
2017-08-11 | [5 empty] | Imogen NA
2017-08-12 | Week 2 | Community Cast Rehearsals | 1 | Holy Apostle |  | Imogen NA
2017-08-13 | Week 2 | Community Cast Rehearsals | 1 | Holy Apostle |  | Imogen NA
2017-08-14 | [5 empty] | Imogen NA
2017-08-15 | [5 empty] | Imogen NA
2017-08-16 | [5 empty] | Imogen NA
2017-08-17 | [5 empty] | Imogen NA
2017-08-18 | [5 empty] | Imogen NA
2017-08-19 | Week 3 | Community Cast Rehearsals | 1 | Holy Apostle |  | Imogen NA
2017-08-20 | Week 3 | Community Cast Rehearsals | 1 | Holy Apostle |  | Imogen NA
2017-08-21 | [5 empty] | Imogen NA
2017-08-22 | [5 empty] | Imogen NA
2017-08-23 | [5 empty] | Imogen returns
2017-08-24
2017-08-25
2017-08-26 | Week 4 | Community Cast Rehearsals | 1 | Holy Apostle
2017-08-27 | Week 4 | Community Cast Rehearsals | 1 | Holy Apostle
2017-08-28
2017-08-29
2017-08-30
2017-08-31
2017-09-01
2017-09-02 | Week 5 | Community Cast Rehearsals | 1 | Holy Apostle
2017-09-03 | Week 5 | Community Cast Rehearsals | 1 | Holy Apostle
2017-09-04
2017-09-05
2017-09-06
2017-09-07
2017-09-08
2017-09-09 | Week 6 | Community Cast Rehearsals | 1 | Holy Apostle
2017-09-10 | Week 6 | Community Cast Rehearsals | 1 | Holy Apostle
2017-09-11
2017-09-12
2017-09-13
2017-09-14
2017-09-15
2017-09-16 | Week 7 | Community Cast Rehearsals | 1 | Holy Apostle
2017-09-17 | Week 7 | Community Cast Rehearsals | 1 | Holy Apostle
2017-09-18
2017-09-19
2017-09-20
2017-09-21
2017-09-22
2017-09-23 | Week 8 | Community Cast Rehearsals | 1 | Holy Apostle
2017-09-24 | Week 8 | Community Cast Rehearsals | 1 | Holy Apostle
2017-09-25
2017-09-26
2017-09-27
2017-09-28
2017-09-29
2017-09-30 | Week 9 | Community Cast Rehearsals | 1 | Holy Apostle
2017-10-01 | Week 9 | Community Cast Rehearsals / Adrian performing in Hull | 1 | Holy Apostle
2017-10-02 | Rehearsal Week 1 | Professional Cast rehearse in Manchester |  | Manchester |  |  | TBC
2017-10-03 |  | Professional Cast rehearse in Manchester |  | Manchester
2017-10-04 |  | Professional Cast rehearse in Manchester |  | Manchester
2017-10-05 |  | Professional Cast rehearse in Manchester |  | Manchester
2017-10-06 |  | Professional Cast rehearse in Manchester |  | Manchester
2017-10-07 | Week 10 | Community Cast Rehearsals | 1 | Holy Apostle
2017-10-08 | Week 10 | Community Cast Rehearsals | 1 | Holy Apostle
2017-10-09 | Rehearsal Week 2 | Professional Cast rehearse in Manchester |  | Manchester |  |  | TBC
2017-10-10 |  | Professional Cast rehearse in Manchester |  | Manchester
2017-10-11 |  | Professional Cast rehearse in Manchester |  | Manchester
2017-10-12 |  | Professional Cast rehearse in Manchester |  | Manchester
2017-10-13 |  | Professional Cast rehearse in Manchester |  | Manchester
2017-10-14 | Week 11 | Community Cast Rehearsals | 1
2017-10-15 | Week 11 | Community Cast Rehearsals | 1
2017-10-16 | Rehearsal Week 3 | Professional Cast rehearse in Hull |  | Holy Apostle | 10am - 5pm; 6 - 9pm |  | TBC | Composer / MD rehearse in Hull (2 Days)
2017-10-17 |  | Professional Cast rehearse in Hull |  | Holy Apostle | 10am - 5pm; 6 - 9pm
| Week 12 | Joined by Community Cast in the evening | 1 | Holy Apostle | 6 - 9 pm |  |  | NB First time for whole company to be together - professional & community cast
2017-10-18 |  | Professional Cast rehearse in Hull |  | Holy Apostle | 10am - 5pm; 6 - 9pm
2017-10-19 |  | Professional Cast rehearse in Hull |  | Holy Apostle | 10am - 5pm; 6 - 9pm
| Week 12 | Joined by Community Cast in the evening | 1 | Holy Apostle | 6 - 9 pm
2017-10-20 |  | Professional Cast rehearse in Hull |  | Holy Apostle | 10am - 5pm; 6 - 9pm
2017-10-21 |  | Professional Cast rehearse in Hull |  | Holy Apostle | 10am - 5pm
| Week 12 | Joined by Community Cast all day | 1 | Holy Apostle | 10am - 5pm
2017-10-22 |  | Day off |  |  | No Call
2017-10-30 | Tech Week | Professional Cast rehearse in Hull |  | Reh Sp 2 | 10am - 5pm; 6 - 9pm |  | Technical Work | Composer/MD rehearse in Hull (full week)
|  | Joined by Community Cast | 1 | Reh Sp 2 | 5 - 9pm
2017-10-31 |  | Technical Rehearsals: Professional Cast |  | Reh Sp 2 - AM Guildhall - PM | 10am - 5pm; 6 - 9pm |  | Tech Sessions | call times for community cast TBC - as many will be working during day
|  | Joined by Community Cast | 1 | Guildhall | 5 - 9pm
2017-11-01 |  | Technical Rehearsals: Professional Cast |  | Guildhall | 10am - 5pm; 6 - 9pm |  | Tech Sessions
|  | Joined by Community Cast | 1 | Guildhall | 5 - 9pm
2017-11-02 |  | Technical Rehearsals: Professional Cast |  | Guildhall | 10am - 5pm; 6 - 9pm |  | Tech Sessions
|  | Joined by Community Cast | 1 | Guildhall | 5 - 9pm
|  | Full Band Call |  | Guildhall | 10am - 5pm; 6 - 9pm
2017-11-03 |  | Dress Rehearsal - Full Company Call (Cast, Band, Community) |  | Guildhall | 1 - 5pm |  | Tech Session AM
|  | Performance PREVIEW | 1 | Guildhall | 7.30pm
2017-11-04 |  | Full Company Call |  | Reh Sp 2 | 1 - 3.30pm |  | Technical Work
|  | Full Company Call |  | Guildhall | 3.30 - 5pm
|  | Performance PREVIEW | 1 | Guildhall | 7.30pm |  |  | Astronomical twilight 5:31pm
2017-11-05 |  | Total Perfs | 2
2017-11-06 | Performance Week 1 | Tech Work; |  | Guildhall |  |  | Technical Work
No call Professional cast, community cast, band.
2017-11-07 |  | Technical Rehearsals: Professional cast and community cast |  | Guildhall | 2 - 5; 6 - 9pm
2017-11-08 |  | Technical Rehearsals: Professional cast and community cast |  | Guildhall | 2 - 5pm
|  | Performance | 1 |  | 7.30pm
2017-11-09 |  | Performance PRESS | 1 | Guildhall | 7.30pm |  |  | MAY MOVE THIS EARLIER
2017-11-10 |  | Performance | 1 | Guildhall | 5:30pm
|  | Performance | 1 | Guildhall | 7:30pm
2017-11-11 |  | Performance | 1 | Guildhall | 5:30pm
|  | Performance | 1 | Guildhall | 8:30pm
2017-11-12
|  | Total Perfs | 6
2017-11-13 | Performance Week 2 | No Call
2017-11-14 |  | No Call
2017-11-15 |  | Performance | 1 | Guildhall | 7.30pm
2017-11-16 |  | Performance | 1 | Guildhall | 5:30pm
|  | Performance | 1 | Guildhall | 7.30pm
2017-11-17 |  | Performance | 1 | Guildhall | 6pm
|  | Performance | 1 | Guildhall | 7:30pm
2017-11-18 |  | Performance FINAL | 1 | Guildhall | 7:30pm
2017-11-19
|  | Total Perfs | 6
Get Out
2017-11-20 |  | Get Out
2017-11-21 |  | Get Out
2017-11-22 |  | Get Out
2017-11-23 |  | Get Out
2017-11-24 |  | Get Out
2017-11-25 |  | Get Out
2017-11-26 |  | Get Out
|  | Community Rehearsal Days / Sessions | 22
|  | Professional and Community Rehearsal Days / Sessions | 7
|  | Performances in total | 14
Formulas:
W/C = SUM([W/C, row above]+7)