**TITANIUM FIREWORKS**

**FEE:** £50,000 to be paid on receipt of invoice, with future payments subject to final budget confirmation

**TERMS:** As agreed in the terms and conditions of the Event & Production Management & Delivery Framework

**GOODS & SERVICES TO BE PROVIDED:**

* Pre-Production
* Design, Programming and simulation
* Health and Safety
* Production and sequencing of fireworks
* Security (at George Dock)
* Equipment Transport
* Insurance
* Radios (comms)
* Dock Infrastructure
* Firing System
* Firing Equipments
* Fireworks
* Management Fee
* Crew (including wages, per diems, transport and accommodation)

**TIMETABLE OF DELIVERY**

|  |  |
| --- | --- |
| **31 October 2016** | Delivery of Design and Simulation to Hull 2017 Team |
| **7 November 2016** | Design sign off by Hull 2017 Team |
| **28 – 31 December 2016** | Load in, George Dock, Hull |
| **1January 2017** | Show Day – Display commences 20:17 |
| **2 – 3 January 2017** | Load Out and dock site handover to ABP |
| **January 2017** | Debrief |